## Executive
Initiative | Owner | Status | Priority | Target Date | Deployment State | Dependency | Executive Note | Next Decision
Stabilize active database connection | Founder + Engineering | Pending | P0 | 2026-05-02 | Not complete | Working DATABASE_URL and reachable Postgres/Neon instance | This is the main blocker for migration and local validation | Choose and lock the active DB provider
Ship real admin control plane | Engineering | In Progress | P0 | 2026-05-04 | Local only | Stable database plus clean validation | Separate admin shell, user management, security, and super-admin system views now exist locally | Validate and choose ship batch
Validate stakeholder workspace provisioning | Founder + Engineering | In Progress | P0 | 2026-05-05 | Local only | Admin control-plane validation | Founder can now seed stakeholder workspaces and initial admins without surrendering SUPER_ADMIN | Approve stakeholder onboarding flow
Apply HR/Projects/Inventory Prisma migration | Engineering | In Progress | P0 | 2026-05-03 | Local only | Stable database connection | Migration exists locally but has not been applied successfully | Run migration after DB is fixed
Validate HR module end-to-end | Engineering + HR Ops | In Progress | P0 | 2026-05-05 | Local only | Migration applied | HR routes and UI rewires exist locally | Approve HR release batch after validation
Validate Projects module end-to-end | Engineering + Operations | In Progress | P0 | 2026-05-06 | Local only | Migration applied | Projects routes and UI rewires exist locally | Approve Projects release batch after validation
Validate Inventory module end-to-end | Engineering + Operations | In Progress | P0 | 2026-05-07 | Local only | Migration applied | Inventory routes and UI rewires exist locally | Approve Inventory release batch after validation
Commit and push backend conversion batch | Engineering | Pending | P0 | 2026-05-08 | Not started | Successful module validation | Large local worktree should be shipped in a controlled batch | Push only clean backend conversion work
Redeploy Render with new backend modules | Engineering + Founder | Pending | P0 | 2026-05-09 | Not started | Committed backend batch on main | Render is behind local backend work | Deploy after push and smoke test
Finish production Google OAuth setup | Founder | Pending | P1 | 2026-05-12 | Not complete | Live Google credentials | Code support exists already | Decide whether Google login remains in launch scope
Finish SMTP configuration | Founder | Pending | P1 | 2026-05-13 | Not complete | SMTP provider credentials | Email/report delivery path exists in code | Choose SMTP provider and test
Finish Cloudinary configuration | Founder | Pending | P1 | 2026-05-13 | Not complete | Cloudinary credentials | Upload flows exist but depend on env values | Complete production media path
Validate AI provider setup in production | Founder + Engineering | Pending | P0 | 2026-05-14 | Partially complete | Live API keys | Provider routing exists, but production behavior needs full validation | Choose primary provider and confirm fallback strategy
Ship tenant lifecycle and invite acceptance | Engineering | Pending | P0 | 2026-05-16 | Not started | Founder-controlled admin base plus stable DB | Stakeholder admins need a complete acceptance and workspace-lifecycle flow, not just seeded records | Prioritize invite acceptance and org lifecycle controls
Enforce action-level RBAC across modules | Engineering + Security | Pending | P0 | 2026-05-18 | Not started | Admin/auth groundwork | Platform credibility requires permissions by action, not just page access | Define the permission matrix and start enforcement
Stand up observability and recovery basics | Engineering + Security | Pending | P0 | 2026-05-19 | Not started | Stable deploy path | Without error tracking, alerting, and restore discipline, production incidents will be opaque | Choose monitoring stack and backup discipline
Build data import/export and recovery controls | Engineering + Operations | Pending | P1 | 2026-05-21 | Not started | Stable DB and admin surfaces | Customers will expect fast onboarding and safe recovery workflows | Scope CSV importers, export center, and soft-delete recovery
Add billing and plan entitlements foundation | Founder + Engineering | Pending | P1 | 2026-05-24 | Not started | Workspace model and admin controls | Commercial rollout needs seat logic and plan-aware feature access | Decide initial pricing/entitlement model
Ship support and customer-success layer | Product + Engineering | Pending | P1 | 2026-05-27 | Not started | Admin and observability foundation | Support needs help center, audited support access, and customer health views | Choose the first support experience to implement
Complete stakeholder pitch readiness gate | Founder + Engineering | Pending | P0 | 2026-05-28 | Not started | Admin, DB, observability, and core validations | You need a deliberate go/no-go gate before serious stakeholder access | Review the pitch-readiness document and score the platform honestly
Tune Civis AI quality for live users | Product + Engineering | Pending | P1 | 2026-05-20 | Ongoing | Stable AI provider configuration | AI is materially improved but still needs polish | Collect real prompts and refine responses
Execute NDPA/VAPT hardening backlog | Engineering + Security | Pending | P0 | 2026-05-23 | Ongoing | Security docs already created | Architecture and API docs exist; implementation backlog remains | Prioritize access control, monitoring, and incident readiness
Keep documentation and OpenAPI in sync | Engineering | Pending | P1 | 2026-05-30 | Ongoing | Feature shipping discipline | Docs exist and should now be maintained with each batch | Make docs updates part of release definition