## In Progress
Phase | Area | Workstream | Task | Status | Deployment State | Priority | Notes | Next Step
Phase 1 | Auth | Security | Password hashing and verification helpers added | In Progress | Local only | P0 | Auth hardening is in local worktree | Commit with next auth/backend batch
Phase 1B | Admin | Control Plane | Separate /admin control-plane shell implemented | In Progress | Local only | P0 | New admin route group and shell exist locally | Validate flow and ship with next backend batch
Phase 1B | Admin | Overview | Live admin overview API and page implemented | In Progress | Local only | P0 | Overview now reflects real org data and audit activity | Validate against live DB and deploy
Phase 1B | Admin | User Management | Workspace user admin page and API expansion implemented | In Progress | Local only | P0 | Admins can create, role-manage, and remove org users with founder lock rules | Validate and deploy
Phase 1B | Admin | Workspace Controls | Workspace settings admin page and API implemented | In Progress | Local only | P1 | Org settings are now split into admin control plane | Validate and deploy
Phase 1B | Admin | Security Controls | Admin security page implemented | In Progress | Local only | P1 | 2FA coverage, privileged users, and audit visibility are surfaced | Validate and deploy
Phase 1B | Admin | Platform Governance | Super-admin system page and workspace provisioning route implemented | In Progress | Local only | P0 | Founder can create stakeholder workspaces without giving up SUPER_ADMIN | Validate and deploy
Phase 12 | Tenant Lifecycle | Workspace Provisioning | Founder-controlled stakeholder workspace provisioning foundation started | In Progress | Local only | P0 | Super-admin can seed workspaces and initial admins, but acceptance and lifecycle are still incomplete | Validate and expand into full tenant lifecycle
Phase 12 | Tenant Lifecycle | Authorization | Founder lock and workspace-scoped admin boundaries started | In Progress | Local only | P0 | Role boundaries now exist in admin flows, but action-level RBAC is not complete | Extend into module-by-module permission enforcement
Phase 8 | HR | Backend Conversion | HR API routes added (employees, payroll, attendance, positions) | In Progress | Local only | P0 | Routes exist in local worktree | Apply migration, test, then commit
Phase 8 | HR | Frontend Rewire | HR page rewritten to call /api/hr/* | In Progress | Local only | P0 | UI is being moved off mock/local-only state | Validate with live DB
Phase 8 | HR | Data Quality | HR scorecard/compliance views present | In Progress | Local only | P1 | Support components exist locally | Finish polish and validation
Phase 8 | Projects | Backend Conversion | Projects API routes added | In Progress | Local only | P0 | /api/projects and /api/projects/tasks exist locally | Apply migration, test, then commit
Phase 8 | Projects | Frontend Rewire | Projects page rewritten to use live API | In Progress | Local only | P0 | Project board/task/timeline are wired toward live data | Validate with live DB
Phase 8 | Inventory | Backend Conversion | Inventory API routes added | In Progress | Local only | P0 | Products, stock, orders routes exist locally | Apply migration, test, then commit
Phase 8 | Inventory | Frontend Rewire | Inventory page rewritten to use live API | In Progress | Local only | P0 | Tables are wired toward live data | Validate with live DB
Phase 8 | Shared Backend | Seed Data | Module seed helper added for HR/Projects/Inventory | In Progress | Local only | P1 | Local seed helper exists | Keep only as controlled dev/demo behavior
Phase 8 | Shared Backend | Access Control | Org ownership checks added to new HR/Projects/Inventory routes | In Progress | Local only | P0 | Mutation routes were tightened locally | Ship with backend conversion commit
Phase 9 | Infrastructure | Database | Pending migration created for HR/Projects/Inventory backend | In Progress | Local only | P0 | Migration folder exists locally | Apply migration to active database