## Pending
Phase | Area | Workstream | Task | Status | Deployment State | Priority | Notes | Next Step
Phase 9 | Infrastructure | Database | Active DATABASE_URL is stable and reachable | Pending | Not complete | P0 | Recent Prisma migrate attempts failed with P1001 | Fix DB provider/credentials first
Phase 9 | Infrastructure | Deployment | Admin control-plane batch committed and pushed | Pending | Not started | P0 | New /admin shell and APIs are local only | Ship alongside backend conversion or in a clean isolated batch
Phase 9 | Infrastructure | Deployment | Render deployment synced with new admin control plane | Pending | Not started | P0 | Stakeholder admin experience is not live until deploy completes | Deploy after push and smoke test
Phase 9 | Infrastructure | Deployment | Local HR/Projects/Inventory backend work committed and pushed | Pending | Not started | P0 | Worktree is ahead of main | Commit a clean backend batch after DB validation
Phase 9 | Infrastructure | Deployment | Render deployment synced with latest local backend conversion | Pending | Not started | P0 | Render is behind current local backend work | Deploy after commit/push
Phase 10 | Integrations | Auth | Production Google OAuth credentials configured | Pending | Not complete | P1 | Code support exists, env still needs live values | Add production client ID/secret
Phase 10 | Integrations | Email | SMTP configured for real notifications and report delivery | Pending | Not complete | P1 | Nodemailer path exists | Add SMTP env values and test delivery
Phase 10 | Integrations | Uploads | Cloudinary configured for production uploads | Pending | Not complete | P1 | Upload path exists but depends on env | Add Cloudinary env values and test portal/gallery/docs
Phase 10 | Integrations | AI | Live AI provider keys configured | Pending | Partially complete | P0 | Provider routing exists but production keys may not be stable | Set and validate chosen providers
Phase 10 | Integrations | Payments | Paystack integration configured if required | Pending | Not complete | P2 | Env placeholders exist | Decide scope and implement if needed
Phase 11 | Quality | AI Quality | Continue tuning AI naturalness and business usefulness | Pending | Ongoing | P1 | AI is improved but still needs product-quality refinement | Use real user prompts and tighten responses
Phase 11 | Quality | Security | Execute remaining security hardening/VAPT backlog | Pending | Ongoing | P0 | Docs exist but many controls remain to implement | Run phased hardening plan
Phase 11 | Quality | Operations | Keep docs and OpenAPI spec aligned with shipped code | Pending | Ongoing | P1 | Docs now exist and need maintenance discipline | Update docs in every feature batch
Phase 11 | Quality | Release Discipline | Separate committed production-ready work from local experiments | Pending | Ongoing | P0 | Local worktree is carrying many in-progress changes | Ship smaller isolated batches
Phase 12 | Tenant Lifecycle | Workspace Provisioning | Invite acceptance flow for seeded users implemented | Pending | Not started | P0 | Stakeholder admins can be created, but acceptance/onboarding is not finished | Build invite acceptance and completion flow
Phase 12 | Tenant Lifecycle | Workspace Access | Multi-workspace membership and org switching implemented | Pending | Not started | P0 | Founder/support workflows will need to move across workspaces cleanly | Design membership model and switcher
Phase 12 | Tenant Lifecycle | Workspace Governance | Workspace suspension, archive, and restore controls implemented | Pending | Not started | P1 | You need a lifecycle for dormant or non-compliant stakeholder orgs | Add org status controls and UI
Phase 12 | Tenant Lifecycle | Entitlements | Org-level feature flags and lifecycle states implemented | Pending | Not started | P1 | Required for staged rollout and plan control | Add feature flag and org state model
Phase 12 | Tenant Lifecycle | Authorization | Action-level RBAC matrix enforced across modules | Pending | Not started | P0 | Current auth is stronger, but not yet a full action matrix | Define and enforce per-action permissions
Phase 13 | Commercial | Billing | Seat and entitlement model implemented | Pending | Not started | P1 | Stakeholder workspaces need plan-aware limits | Define seat model and enforcement
Phase 13 | Commercial | Billing | Billing and subscription admin console implemented | Pending | Not started | P1 | Admins need visibility into plan and seats | Build billing summary and controls
Phase 13 | Commercial | Feature Gating | Plan-aware feature gating implemented | Pending | Not started | P1 | Needed to sell multiple tiers without code forks | Add entitlements to routes and UI
Phase 13 | Commercial | Lifecycle | Trial, upgrade, and downgrade flows implemented | Pending | Not started | P2 | Commercial readiness improves with self-service lifecycle | Add commercial lifecycle rules
Phase 14 | Reliability | Observability | Production error tracking and alerting configured | Pending | Not started | P0 | You should know when auth, AI, uploads, or DB fail in production | Configure monitoring and alerting
Phase 14 | Reliability | Observability | Structured logs and uptime monitoring configured | Pending | Not started | P1 | Support and operations need visibility into live failures | Add log aggregation and uptime checks
Phase 14 | Reliability | Async Work | Background jobs and queue system implemented | Pending | Not started | P1 | Digests, webhooks, and retries should not depend on request-response timing | Add async job infrastructure
Phase 14 | Reliability | Recovery | Backup and restore workflow documented and tested | Pending | Not started | P0 | Production data safety is not optional | Define backup plan and run restore drills
Phase 14 | Reliability | Recovery | Incident response runbook operationalized | Pending | Not started | P1 | The docs exist, but the operating motion does not yet | Create and test response workflow
Phase 15 | Data Governance | Import/Export | CSV importers for CRM, HR, inventory, and accounting implemented | Pending | Not started | P1 | Real customers will want to move data in fast | Build import tools and mapping UX
Phase 15 | Data Governance | Import/Export | Admin export center for operational and compliance data implemented | Pending | Not started | P1 | Stakeholders will need consistent exports beyond isolated reports | Add central export surface
Phase 15 | Data Governance | Recovery | Soft delete and record recovery flows implemented | Pending | Not started | P1 | Accidental deletion without recovery will hurt trust | Add reversible delete patterns
Phase 15 | Data Governance | Compliance | Data retention and purge controls implemented | Pending | Not started | P1 | Needed for governance and NDPA discipline | Define retention policy and jobs
Phase 15 | Data Governance | Compliance | NDPA/privacy request workflow implemented | Pending | Not started | P1 | Privacy requests should be operational, not only documented | Add request handling workflow
Phase 15 | Data Governance | Governance | Approval center for sensitive actions implemented | Pending | Not started | P1 | High-risk actions need approvals and evidence | Build approval center and audit tie-in
Phase 15 | Data Governance | Branding | White-label and enterprise branding controls implemented | Pending | Not started | P2 | Important for polished stakeholder rollout, but not a launch blocker | Add branding controls later
Phase 16 | Support | Customer Success | In-product help center and onboarding content implemented | Pending | Not started | P2 | Users need a support surface that does not depend on you manually answering everything | Build help center and guides
Phase 16 | Support | Support Ops | Support impersonation with audit trail implemented | Pending | Not started | P1 | Support needs controlled access for troubleshooting | Add audited impersonation or support sessions
Phase 16 | Support | Customer Success | Customer usage and health analytics implemented | Pending | Not started | P2 | Useful for renewals and stakeholder expansion | Add adoption and health reporting
Phase 16 | Support | Communication | Release notes and changelog workflow implemented | Pending | Not started | P2 | Customers should see product progress clearly | Add changelog discipline
Phase 16 | Go-To-Market | Quality | Accessibility and mobile QA sweep completed | Pending | Not started | P1 | Pitching stakeholders on unstable mobile/accessibility experiences is risky | Run QA sweep and fix findings
Phase 16 | Go-To-Market | Readiness | Stakeholder pitch readiness gate completed | Pending | Not started | P0 | You need a formal go/no-go checklist before handing this to serious stakeholders | Use the pitch-readiness document as the gate