## Pitch Readiness
Tier | Area | Requirement | Status | Priority | Notes
Must Have | Platform Control | Founder remains the only permanent SUPER_ADMIN | In Progress | P0 | Policy and local enforcement exist; must be validated on live deploy
Must Have | Platform Control | Stakeholder admins are restricted to their own workspace | In Progress | P0 | Admin boundaries exist locally; validate on live deploy
Must Have | Platform Control | Admin pages are live on deployed environment | Pending | P0 | New control plane is local until committed and deployed
Must Have | Platform Control | Workspace admin user management works on deployed environment | Pending | P0 | Needs live validation after deploy
Must Have | Data and Backend | Database connection is stable and reachable | Pending | P0 | Current DB connectivity is the main blocker
Must Have | Data and Backend | Pending migrations are applied successfully | Pending | P0 | Required before broader live validation
Must Have | Data and Backend | Core module data persists correctly against live DB | Pending | P0 | HR, Projects, Inventory still need end-to-end live validation
Must Have | Security Baseline | Role boundaries are enforced server-side | In Progress | P0 | Improved locally; still needs broader module-by-module hardening
Must Have | Security Baseline | Audit logs capture admin-critical actions | In Progress | P0 | Admin actions now audit locally; validate and broaden coverage
Must Have | Product Stability | Critical pages do not throw runtime errors in demo path | In Progress | P0 | Production build passes; still validate deployed flow
Should Have Before Paid Pilot | Identity and Access | Invite acceptance flow for seeded users | Pending | P0 | Stakeholder onboarding needs completion flow
Should Have Before Paid Pilot | Identity and Access | Stable Google OAuth or clearly supported credentials flow | Pending | P1 | Decide the production sign-in path and validate it
Should Have Before Paid Pilot | Identity and Access | Full 2FA validation against live database | Pending | P1 | Route surface exists; live validation still needed
Should Have Before Paid Pilot | Production Integrations | SMTP configured and tested | Pending | P1 | Required for notifications and digests
Should Have Before Paid Pilot | Production Integrations | Cloudinary or equivalent upload storage configured and tested | Pending | P1 | Required for portal/docs/gallery upload credibility
Should Have Before Paid Pilot | Reliability | Error tracking configured | Pending | P0 | You need visibility into production failures
Should Have Before Paid Pilot | Reliability | Backup and restore plan tested | Pending | P0 | Production data safety must be operational
Should Have Before Paid Pilot | Governance | Security hardening backlog started in implementation | Pending | P1 | NDPA/VAPT should move from docs into code/ops
Pitch-Ready Next | Data Governance | CSV importers for CRM/HR/Inventory/Accounting | Pending | P1 | Important for real onboarding speed
Pitch-Ready Next | Data Governance | Export center for operational/compliance workflows | Pending | P1 | Stakeholders will ask for reliable exports
Pitch-Ready Next | Recovery | Soft delete and record recovery | Pending | P1 | Protects trust after mistakes
Pitch-Ready Next | Support | In-product help center | Pending | P2 | Reduces dependence on founder support
Pitch-Ready Next | Support | Support impersonation with audit trail | Pending | P1 | Important for troubleshooting and customer success
Pitch-Ready Next | Commercial | Billing and seat visibility for admins | Pending | P1 | Important as soon as pricing is formalized
Later | Enterprise | White-label and enterprise branding controls | Pending | P2 | Useful for premium deals but not first blocker
Later | Commercial | Advanced subscription self-service | Pending | P2 | Can follow initial controlled rollout
Later | Governance | Expanded approval center for sensitive actions | Pending | P2 | Important as complexity grows
Later | Brand | Landing page and marketing-site redesign | Pending | P2 | Important for conversion and brand perception, but not the first platform blocker