## Master
Phase | Area | Workstream | Task | Status | Deployment State | Priority | Notes | Next Step
Phase 0 | Foundation | Platform Setup | Next.js 16 app structure is in place | Done | On main | P0 | Public pages and dashboard shell already exist | Maintain and extend
Phase 0 | Foundation | Platform Setup | Prisma schema and Postgres integration are in place | Done | On main | P0 | Core relational data model exists | Keep schema synced with migrations
Phase 0 | Foundation | Build System | Production build switched to webpack for stability | Done | Local and expected for next deploy | P0 | Local build passes via webpack path | Commit and deploy with next backend batch
Phase 0 | Foundation | Documentation | Project dossier created | Done | On main | P1 | Snapshot-level project documentation exists | Keep updated after major releases
Phase 0 | Foundation | Documentation | Product overview created | Done | On main | P1 | Business-facing project summary exists | Refine for investor/client use if needed
Phase 0 | Foundation | Documentation | Technical handoff created | Done | On main | P1 | Developer-facing handoff doc exists | Update after backend shipping
Phase 0 | Foundation | Documentation | Platform readiness tracker expanded to full product scope | Done | Local only | P1 | Checklist now explicitly tracks missing platform layers like admin, tenant lifecycle, billing, observability, support, and enterprise governance | Keep updated as scope evolves
Phase 1 | Auth | Authentication | NextAuth credentials login implemented | Done | On main | P0 | Credentials flow exists | Keep testing against live DB
Phase 1 | Auth | Authentication | Google OAuth support path implemented | Done | On main | P1 | Provider support exists in code | Add production credentials
Phase 1 | Auth | Authentication | 2FA routes implemented | Done | Mostly local/in repo | P1 | Setup, verify, disable, verify-login routes exist | Validate end-to-end with live DB
Phase 1 | Auth | Authorization | Role model implemented (SUPER_ADMIN, ADMIN, USER) | Done | On main | P0 | Role enum and session role flow exist | Expand RBAC per module/action
Phase 1 | Auth | Security | Password hashing and verification helpers added | In Progress | Local only | P0 | Auth hardening is in local worktree | Commit with next auth/backend batch
Phase 1B | Admin | Control Plane | Separate /admin control-plane shell implemented | In Progress | Local only | P0 | New admin route group and shell exist locally | Validate flow and ship with next backend batch
Phase 1B | Admin | Overview | Live admin overview API and page implemented | In Progress | Local only | P0 | Overview now reflects real org data and audit activity | Validate against live DB and deploy
Phase 1B | Admin | User Management | Workspace user admin page and API expansion implemented | In Progress | Local only | P0 | Admins can create, role-manage, and remove org users with founder lock rules | Validate and deploy
Phase 1B | Admin | Workspace Controls | Workspace settings admin page and API implemented | In Progress | Local only | P1 | Org settings are now split into admin control plane | Validate and deploy
Phase 1B | Admin | Security Controls | Admin security page implemented | In Progress | Local only | P1 | 2FA coverage, privileged users, and audit visibility are surfaced | Validate and deploy
Phase 1B | Admin | Platform Governance | Super-admin system page and workspace provisioning route implemented | In Progress | Local only | P0 | Founder can create stakeholder workspaces without giving up SUPER_ADMIN | Validate and deploy
Phase 2 | CRM | Core CRM | Contacts CRUD implemented | Done | On main | P0 | API and page support exist | Continue UX improvement
Phase 2 | CRM | Core CRM | Companies CRUD implemented | Done | On main | P0 | API and page support exist | Continue UX improvement
Phase 2 | CRM | Core CRM | Deals CRUD implemented | Done | On main | P0 | API and page support exist | Continue UX improvement
Phase 2 | CRM | Customization | Custom CRM field system implemented | Done | On main | P1 | Supports text, number, currency, date, select, multiselect, checkbox | Improve field editor UX
Phase 2 | CRM | Automation | CRM follow-up generation endpoint implemented | Done | On main | P1 | Follow-up generation route exists | Keep tuning AI quality
Phase 2 | CRM | Reporting | CRM reports and dashboard views implemented | Done | On main | P1 | Reporting surface exists | Improve accuracy/visual polish
Phase 3 | Accounting | Finance Core | Invoices CRUD implemented | Done | On main | P0 | Accounting API routes exist | Continue real-world validation
Phase 3 | Accounting | Finance Core | Expenses CRUD implemented | Done | On main | P0 | Accounting API routes exist | Continue real-world validation
Phase 3 | Accounting | Reporting | Report export routes implemented | Done | On main | P1 | Export and summary endpoints exist | Validate data accuracy with live DB
Phase 3 | Accounting | Reporting | Digest/reporting endpoints implemented | Done | On main | P1 | Digest and summary routes exist | Connect to SMTP for email delivery
Phase 4 | Operations | Ops Control | Ops command center implemented | Done | On main | P1 | Operations route/page exist | Continue UX and live data tuning
Phase 4 | Operations | Automation | Workflow endpoints implemented | Done | On main | P1 | Automation workflow support exists | Add more real workflows
Phase 4 | Operations | Automation | Playbooks implemented | Done | On main | P1 | Playbook route/page exist | Keep expanding playbook library
Phase 4 | Operations | Governance | Decision trails and rollback routes implemented | Done | On main | P1 | Decision trail and rollback endpoints exist | Continue auditability improvements
Phase 4 | Operations | Governance | Audit logging implemented | Done | On main | P0 | Audit helper and route exist | Broaden action coverage
Phase 4 | Operations | Integrations | Webhook endpoints implemented | Done | On main | P1 | Webhook route exists | Lock down and document secrets/rotation
Phase 5 | Portal | Client Collaboration | Client portal implemented | Done | On main | P1 | Portal routes, page, updates, docs, approvals exist | Improve production UX
Phase 5 | Portal | Client Collaboration | Portal updates implemented | Done | On main | P1 | Update routes exist | Continue UI polish
Phase 5 | Portal | Client Collaboration | Portal documents implemented | Done | On main | P1 | Document route exists | Finish real upload path with Cloudinary
Phase 5 | Portal | Client Collaboration | Portal approvals implemented | Done | On main | P1 | Approval route exists | Test approval flows against live DB
Phase 6 | AI | Assistant Core | /api/ai/chat implemented | Done | On main | P0 | Primary AI route exists | Keep prompt and tool quality improving
Phase 6 | AI | Assistant Core | /api/ai/conversations implemented | Done | On main | P1 | Conversation alias route exists | Use for future thread persistence
Phase 6 | AI | Provider Routing | OpenAI/Anthropic/Gemini provider routing implemented | Done | On main | P0 | Provider selection logic exists | Add/verify live keys
Phase 6 | AI | User Experience | Global AI coach/popover implemented | Done | On main | P1 | AI guide is embedded across pages | Refine guidance and humor balance
Phase 6 | AI | User Experience | AI guided navigation actions implemented | Done | On main | P1 | Model can route users to modules | Improve page-aware highlighting
Phase 6 | AI | Productivity | Email drafting implemented | Done | On main | P1 | Email mode exists | Improve draft templates per department
Phase 6 | AI | Reliability | Fallback behavior for provider/DB outages implemented | Done | On main | P0 | Fallback protects UX when systems are unavailable | Reduce robotic fallback tone further
Phase 6 | AI | Quality | Natural free-form conversation upgraded | Done | On main | P1 | Model-first flow replaced rigid menus | Continue real-world prompt tuning
Phase 7 | Security | Architecture | Security architecture doc created | Done | On main | P1 | System architecture doc exists | Maintain as system evolves
Phase 7 | Security | Architecture | Endpoint inventory doc created | Done | On main | P1 | Endpoint inventory exists | Update after new APIs
Phase 7 | Security | Compliance | NDPA/VAPT hardening plan created | Done | On main | P1 | Security roadmap doc exists | Execute the hardening backlog
Phase 7 | Security | API Docs | OpenAPI spec created | Done | On main | P1 | Swagger-importable YAML exists | Keep synchronized with routes
Phase 7 | Security | API Docs | In-app API docs page implemented | Done | On main | P1 | /dashboard/docs/api exists | Use as internal reference
Phase 8 | HR | Backend Conversion | HR API routes added (employees, payroll, attendance, positions) | In Progress | Local only | P0 | Routes exist in local worktree | Apply migration, test, then commit
Phase 8 | HR | Frontend Rewire | HR page rewritten to call /api/hr/* | In Progress | Local only | P0 | UI is being moved off mock/local-only state | Validate with live DB
Phase 8 | HR | Data Quality | HR scorecard/compliance views present | In Progress | Local only | P1 | Support components exist locally | Finish polish and validation
Phase 8 | Projects | Backend Conversion | Projects API routes added | In Progress | Local only | P0 | /api/projects and /api/projects/tasks exist locally | Apply migration, test, then commit
Phase 8 | Projects | Frontend Rewire | Projects page rewritten to use live API | In Progress | Local only | P0 | Project board/task/timeline are wired toward live data | Validate with live DB
Phase 8 | Inventory | Backend Conversion | Inventory API routes added | In Progress | Local only | P0 | Products, stock, orders routes exist locally | Apply migration, test, then commit
Phase 8 | Inventory | Frontend Rewire | Inventory page rewritten to use live API | In Progress | Local only | P0 | Tables are wired toward live data | Validate with live DB
Phase 8 | Shared Backend | Seed Data | Module seed helper added for HR/Projects/Inventory | In Progress | Local only | P1 | Local seed helper exists | Keep only as controlled dev/demo behavior
Phase 8 | Shared Backend | Access Control | Org ownership checks added to new HR/Projects/Inventory routes | In Progress | Local only | P0 | Mutation routes were tightened locally | Ship with backend conversion commit
Phase 9 | Infrastructure | Database | Pending migration created for HR/Projects/Inventory backend | In Progress | Local only | P0 | Migration folder exists locally | Apply migration to active database
Phase 9 | Infrastructure | Database | Active DATABASE_URL is stable and reachable | Pending | Not complete | P0 | Recent Prisma migrate attempts failed with P1001 | Fix DB provider/credentials first
Phase 9 | Infrastructure | Deployment | Admin control-plane batch committed and pushed | Pending | Not started | P0 | New /admin shell and APIs are local only | Ship alongside backend conversion or in a clean isolated batch
Phase 9 | Infrastructure | Deployment | Render deployment synced with new admin control plane | Pending | Not started | P0 | Stakeholder admin experience is not live until deploy completes | Deploy after push and smoke test
Phase 9 | Infrastructure | Deployment | Local HR/Projects/Inventory backend work committed and pushed | Pending | Not started | P0 | Worktree is ahead of main | Commit a clean backend batch after DB validation
Phase 9 | Infrastructure | Deployment | Render deployment synced with latest local backend conversion | Pending | Not started | P0 | Render is behind current local backend work | Deploy after commit/push
Phase 10 | Integrations | Auth | Production Google OAuth credentials configured | Pending | Not complete | P1 | Code support exists, env still needs live values | Add production client ID/secret
Phase 10 | Integrations | Email | SMTP configured for real notifications and report delivery | Pending | Not complete | P1 | Nodemailer path exists | Add SMTP env values and test delivery
Phase 10 | Integrations | Uploads | Cloudinary configured for production uploads | Pending | Not complete | P1 | Upload path exists but depends on env | Add Cloudinary env values and test portal/gallery/docs
Phase 10 | Integrations | AI | Live AI provider keys configured | Pending | Partially complete | P0 | Provider routing exists but production keys may not be stable | Set and validate chosen providers
Phase 10 | Integrations | Payments | Paystack integration configured if required | Pending | Not complete | P2 | Env placeholders exist | Decide scope and implement if needed
Phase 11 | Quality | AI Quality | Continue tuning AI naturalness and business usefulness | Pending | Ongoing | P1 | AI is improved but still needs product-quality refinement | Use real user prompts and tighten responses
Phase 11 | Quality | Security | Execute remaining security hardening/VAPT backlog | Pending | Ongoing | P0 | Docs exist but many controls remain to implement | Run phased hardening plan
Phase 11 | Quality | Operations | Keep docs and OpenAPI spec aligned with shipped code | Pending | Ongoing | P1 | Docs now exist and need maintenance discipline | Update docs in every feature batch
Phase 11 | Quality | Release Discipline | Separate committed production-ready work from local experiments | Pending | Ongoing | P0 | Local worktree is carrying many in-progress changes | Ship smaller isolated batches
Phase 12 | Tenant Lifecycle | Workspace Provisioning | Invite acceptance flow for seeded users implemented | Pending | Not started | P0 | Stakeholder admins can be created, but acceptance/onboarding is not finished | Build invite acceptance and completion flow
Phase 12 | Tenant Lifecycle | Workspace Access | Multi-workspace membership and org switching implemented | Pending | Not started | P0 | Founder/support workflows will need to move across workspaces cleanly | Design membership model and switcher
Phase 12 | Tenant Lifecycle | Workspace Governance | Workspace suspension, archive, and restore controls implemented | Pending | Not started | P1 | You need a lifecycle for dormant or non-compliant stakeholder orgs | Add org status controls and UI
Phase 12 | Tenant Lifecycle | Entitlements | Org-level feature flags and lifecycle states implemented | Pending | Not started | P1 | Required for staged rollout and plan control | Add feature flag and org state model
Phase 12 | Tenant Lifecycle | Authorization | Action-level RBAC matrix enforced across modules | Pending | Not started | P0 | Current auth is stronger, but not yet a full action matrix | Define and enforce per-action permissions
Phase 13 | Commercial | Billing | Seat and entitlement model implemented | Pending | Not started | P1 | Stakeholder workspaces need plan-aware limits | Define seat model and enforcement
Phase 13 | Commercial | Billing | Billing and subscription admin console implemented | Pending | Not started | P1 | Admins need visibility into plan and seats | Build billing summary and controls
Phase 13 | Commercial | Feature Gating | Plan-aware feature gating implemented | Pending | Not started | P1 | Needed to sell multiple tiers without code forks | Add entitlements to routes and UI
Phase 13 | Commercial | Lifecycle | Trial, upgrade, and downgrade flows implemented | Pending | Not started | P2 | Commercial readiness improves with self-service lifecycle | Add commercial lifecycle rules
Phase 14 | Reliability | Observability | Production error tracking and alerting configured | Pending | Not started | P0 | You should know when auth, AI, uploads, or DB fail in production | Configure monitoring and alerting
Phase 14 | Reliability | Observability | Structured logs and uptime monitoring configured | Pending | Not started | P1 | Support and operations need visibility into live failures | Add log aggregation and uptime checks
Phase 14 | Reliability | Async Work | Background jobs and queue system implemented | Pending | Not started | P1 | Digests, webhooks, and retries should not depend on request-response timing | Add async job infrastructure
Phase 14 | Reliability | Recovery | Backup and restore workflow documented and tested | Pending | Not started | P0 | Production data safety is not optional | Define backup plan and run restore drills
Phase 14 | Reliability | Recovery | Incident response runbook operationalized | Pending | Not started | P1 | The docs exist, but the operating motion does not yet | Create and test response workflow
Phase 15 | Data Governance | Import/Export | CSV importers for CRM, HR, inventory, and accounting implemented | Pending | Not started | P1 | Real customers will want to move data in fast | Build import tools and mapping UX
Phase 15 | Data Governance | Import/Export | Admin export center for operational and compliance data implemented | Pending | Not started | P1 | Stakeholders will need consistent exports beyond isolated reports | Add central export surface
Phase 15 | Data Governance | Recovery | Soft delete and record recovery flows implemented | Pending | Not started | P1 | Accidental deletion without recovery will hurt trust | Add reversible delete patterns
Phase 15 | Data Governance | Compliance | Data retention and purge controls implemented | Pending | Not started | P1 | Needed for governance and NDPA discipline | Define retention policy and jobs
Phase 15 | Data Governance | Compliance | NDPA/privacy request workflow implemented | Pending | Not started | P1 | Privacy requests should be operational, not only documented | Add request handling workflow
Phase 15 | Data Governance | Governance | Approval center for sensitive actions implemented | Pending | Not started | P1 | High-risk actions need approvals and evidence | Build approval center and audit tie-in
Phase 15 | Data Governance | Branding | White-label and enterprise branding controls implemented | Pending | Not started | P2 | Important for polished stakeholder rollout, but not a launch blocker | Add branding controls later
Phase 16 | Support | Customer Success | In-product help center and onboarding content implemented | Pending | Not started | P2 | Users need a support surface that does not depend on you manually answering everything | Build help center and guides
Phase 16 | Support | Support Ops | Support impersonation with audit trail implemented | Pending | Not started | P1 | Support needs controlled access for troubleshooting | Add audited impersonation or support sessions
Phase 16 | Support | Customer Success | Customer usage and health analytics implemented | Pending | Not started | P2 | Useful for renewals and stakeholder expansion | Add adoption and health reporting
Phase 16 | Support | Communication | Release notes and changelog workflow implemented | Pending | Not started | P2 | Customers should see product progress clearly | Add changelog discipline
Phase 16 | Go-To-Market | Quality | Accessibility and mobile QA sweep completed | Pending | Not started | P1 | Pitching stakeholders on unstable mobile/accessibility experiences is risky | Run QA sweep and fix findings
Phase 16 | Go-To-Market | Readiness | Stakeholder pitch readiness gate completed | Pending | Not started | P0 | You need a formal go/no-go checklist before handing this to serious stakeholders | Use the pitch-readiness document as the gate
Phase 17 | Brand | Marketing Site | Landing page redesign completed | Pending | Not started | P2 | Current landing page is not yet strong enough for premium product positioning | Run a full brand and conversion redesign later
Phase 17 | Brand | Positioning | Product messaging and trust-signals upgraded | Pending | Not started | P2 | The product needs clearer premium positioning for stakeholders and buyers | Rewrite positioning and supporting sections

## Executive
Initiative | Owner | Status | Priority | Target Date | Deployment State | Dependency | Executive Note | Next Decision
Stabilize active database connection | Founder + Engineering | Pending | P0 | 2026-05-02 | Not complete | Working DATABASE_URL and reachable Postgres/Neon instance | This is the main blocker for migration and local validation | Choose and lock the active DB provider
Ship real admin control plane | Engineering | In Progress | P0 | 2026-05-04 | Local only | Stable database plus clean validation | Separate admin shell, user management, security, and super-admin system views now exist locally | Validate and choose ship batch
Validate stakeholder workspace provisioning | Founder + Engineering | In Progress | P0 | 2026-05-05 | Local only | Admin control-plane validation | Founder can now seed stakeholder workspaces and initial admins without surrendering SUPER_ADMIN | Approve stakeholder onboarding flow
Apply HR/Projects/Inventory Prisma migration | Engineering | In Progress | P0 | 2026-05-03 | Local only | Stable database connection | Migration exists locally but has not been applied successfully | Run migration after DB is fixed
Validate HR module end-to-end | Engineering + HR Ops | In Progress | P0 | 2026-05-05 | Local only | Migration applied | HR routes and UI rewires exist locally | Approve HR release batch after validation
Validate Projects module end-to-end | Engineering + Operations | In Progress | P0 | 2026-05-06 | Local only | Migration applied | Projects routes and UI rewires exist locally | Approve Projects release batch after validation
Validate Inventory module end-to-end | Engineering + Operations | In Progress | P0 | 2026-05-07 | Local only | Migration applied | Inventory routes and UI rewires exist locally | Approve Inventory release batch after validation
Commit and push backend conversion batch | Engineering | Pending | P0 | 2026-05-08 | Not started | Successful module validation | Large local worktree should be shipped in a controlled batch | Push only clean backend conversion work
Redeploy Render with new backend modules | Engineering + Founder | Pending | P0 | 2026-05-09 | Not started | Committed backend batch on main | Render is behind local backend work | Deploy after push and smoke test
Finish production Google OAuth setup | Founder | Pending | P1 | 2026-05-12 | Not complete | Live Google credentials | Code support exists already | Decide whether Google login remains in launch scope
Finish SMTP configuration | Founder | Pending | P1 | 2026-05-13 | Not complete | SMTP provider credentials | Email/report delivery path exists in code | Choose SMTP provider and test
Finish Cloudinary configuration | Founder | Pending | P1 | 2026-05-13 | Not complete | Cloudinary credentials | Upload flows exist but depend on env values | Complete production media path
Validate AI provider setup in production | Founder + Engineering | Pending | P0 | 2026-05-14 | Partially complete | Live API keys | Provider routing exists, but production behavior needs full validation | Choose primary provider and confirm fallback strategy
Ship tenant lifecycle and invite acceptance | Engineering | Pending | P0 | 2026-05-16 | Not started | Founder-controlled admin base plus stable DB | Stakeholder admins need a complete acceptance and workspace-lifecycle flow, not just seeded records | Prioritize invite acceptance and org lifecycle controls
Enforce action-level RBAC across modules | Engineering + Security | Pending | P0 | 2026-05-18 | Not started | Admin/auth groundwork | Platform credibility requires permissions by action, not just page access | Define the permission matrix and start enforcement
Stand up observability and recovery basics | Engineering + Security | Pending | P0 | 2026-05-19 | Not started | Stable deploy path | Without error tracking, alerting, and restore discipline, production incidents will be opaque | Choose monitoring stack and backup discipline
Build data import/export and recovery controls | Engineering + Operations | Pending | P1 | 2026-05-21 | Not started | Stable DB and admin surfaces | Customers will expect fast onboarding and safe recovery workflows | Scope CSV importers, export center, and soft-delete recovery
Add billing and plan entitlements foundation | Founder + Engineering | Pending | P1 | 2026-05-24 | Not started | Workspace model and admin controls | Commercial rollout needs seat logic and plan-aware feature access | Decide initial pricing/entitlement model
Ship support and customer-success layer | Product + Engineering | Pending | P1 | 2026-05-27 | Not started | Admin and observability foundation | Support needs help center, audited support access, and customer health views | Choose the first support experience to implement
Complete stakeholder pitch readiness gate | Founder + Engineering | Pending | P0 | 2026-05-28 | Not started | Admin, DB, observability, and core validations | You need a deliberate go/no-go gate before serious stakeholder access | Review the pitch-readiness document and score the platform honestly
Redesign landing page and premium positioning | Product + Design + Engineering | Pending | P2 | 2026-06-02 | Not started | Core platform credibility first | The current landing page does not yet match the quality of the product ambition | Treat it as a dedicated brand/conversion redesign later
Tune Civis AI quality for live users | Product + Engineering | Pending | P1 | 2026-05-20 | Ongoing | Stable AI provider configuration | AI is materially improved but still needs polish | Collect real prompts and refine responses
Execute NDPA/VAPT hardening backlog | Engineering + Security | Pending | P0 | 2026-05-23 | Ongoing | Security docs already created | Architecture and API docs exist; implementation backlog remains | Prioritize access control, monitoring, and incident readiness
Keep documentation and OpenAPI in sync | Engineering | Pending | P1 | 2026-05-30 | Ongoing | Feature shipping discipline | Docs exist and should now be maintained with each batch | Make docs updates part of release definition

## Done
Phase | Area | Workstream | Task | Status | Deployment State | Priority | Notes | Next Step
Phase 0 | Foundation | Platform Setup | Next.js 16 app structure is in place | Done | On main | P0 | Public pages and dashboard shell already exist | Maintain and extend
Phase 0 | Foundation | Platform Setup | Prisma schema and Postgres integration are in place | Done | On main | P0 | Core relational data model exists | Keep schema synced with migrations
Phase 0 | Foundation | Build System | Production build switched to webpack for stability | Done | Local and expected for next deploy | P0 | Local build passes via webpack path | Commit and deploy with next backend batch
Phase 0 | Foundation | Documentation | Project dossier created | Done | On main | P1 | Snapshot-level project documentation exists | Keep updated after major releases
Phase 0 | Foundation | Documentation | Product overview created | Done | On main | P1 | Business-facing project summary exists | Refine for investor/client use if needed
Phase 0 | Foundation | Documentation | Technical handoff created | Done | On main | P1 | Developer-facing handoff doc exists | Update after backend shipping
Phase 0 | Foundation | Documentation | Platform readiness tracker expanded to full product scope | Done | Local only | P1 | Checklist now explicitly tracks missing platform layers like admin, tenant lifecycle, billing, observability, support, and enterprise governance | Keep updated as scope evolves
Phase 1 | Auth | Authentication | NextAuth credentials login implemented | Done | On main | P0 | Credentials flow exists | Keep testing against live DB
Phase 1 | Auth | Authentication | Google OAuth support path implemented | Done | On main | P1 | Provider support exists in code | Add production credentials
Phase 1 | Auth | Authentication | 2FA routes implemented | Done | Mostly local/in repo | P1 | Setup, verify, disable, verify-login routes exist | Validate end-to-end with live DB
Phase 1 | Auth | Authorization | Role model implemented (SUPER_ADMIN, ADMIN, USER) | Done | On main | P0 | Role enum and session role flow exist | Expand RBAC per module/action
Phase 2 | CRM | Core CRM | Contacts CRUD implemented | Done | On main | P0 | API and page support exist | Continue UX improvement
Phase 2 | CRM | Core CRM | Companies CRUD implemented | Done | On main | P0 | API and page support exist | Continue UX improvement
Phase 2 | CRM | Core CRM | Deals CRUD implemented | Done | On main | P0 | API and page support exist | Continue UX improvement
Phase 2 | CRM | Customization | Custom CRM field system implemented | Done | On main | P1 | Supports text, number, currency, date, select, multiselect, checkbox | Improve field editor UX
Phase 2 | CRM | Automation | CRM follow-up generation endpoint implemented | Done | On main | P1 | Follow-up generation route exists | Keep tuning AI quality
Phase 2 | CRM | Reporting | CRM reports and dashboard views implemented | Done | On main | P1 | Reporting surface exists | Improve accuracy/visual polish
Phase 3 | Accounting | Finance Core | Invoices CRUD implemented | Done | On main | P0 | Accounting API routes exist | Continue real-world validation
Phase 3 | Accounting | Finance Core | Expenses CRUD implemented | Done | On main | P0 | Accounting API routes exist | Continue real-world validation
Phase 3 | Accounting | Reporting | Report export routes implemented | Done | On main | P1 | Export and summary endpoints exist | Validate data accuracy with live DB
Phase 3 | Accounting | Reporting | Digest/reporting endpoints implemented | Done | On main | P1 | Digest and summary routes exist | Connect to SMTP for email delivery
Phase 4 | Operations | Ops Control | Ops command center implemented | Done | On main | P1 | Operations route/page exist | Continue UX and live data tuning
Phase 4 | Operations | Automation | Workflow endpoints implemented | Done | On main | P1 | Automation workflow support exists | Add more real workflows
Phase 4 | Operations | Automation | Playbooks implemented | Done | On main | P1 | Playbook route/page exist | Keep expanding playbook library
Phase 4 | Operations | Governance | Decision trails and rollback routes implemented | Done | On main | P1 | Decision trail and rollback endpoints exist | Continue auditability improvements
Phase 4 | Operations | Governance | Audit logging implemented | Done | On main | P0 | Audit helper and route exist | Broaden action coverage
Phase 4 | Operations | Integrations | Webhook endpoints implemented | Done | On main | P1 | Webhook route exists | Lock down and document secrets/rotation
Phase 5 | Portal | Client Collaboration | Client portal implemented | Done | On main | P1 | Portal routes, page, updates, docs, approvals exist | Improve production UX
Phase 5 | Portal | Client Collaboration | Portal updates implemented | Done | On main | P1 | Update routes exist | Continue UI polish
Phase 5 | Portal | Client Collaboration | Portal documents implemented | Done | On main | P1 | Document route exists | Finish real upload path with Cloudinary
Phase 5 | Portal | Client Collaboration | Portal approvals implemented | Done | On main | P1 | Approval route exists | Test approval flows against live DB
Phase 6 | AI | Assistant Core | /api/ai/chat implemented | Done | On main | P0 | Primary AI route exists | Keep prompt and tool quality improving
Phase 6 | AI | Assistant Core | /api/ai/conversations implemented | Done | On main | P1 | Conversation alias route exists | Use for future thread persistence
Phase 6 | AI | Provider Routing | OpenAI/Anthropic/Gemini provider routing implemented | Done | On main | P0 | Provider selection logic exists | Add/verify live keys
Phase 6 | AI | User Experience | Global AI coach/popover implemented | Done | On main | P1 | AI guide is embedded across pages | Refine guidance and humor balance
Phase 6 | AI | User Experience | AI guided navigation actions implemented | Done | On main | P1 | Model can route users to modules | Improve page-aware highlighting
Phase 6 | AI | Productivity | Email drafting implemented | Done | On main | P1 | Email mode exists | Improve draft templates per department
Phase 6 | AI | Reliability | Fallback behavior for provider/DB outages implemented | Done | On main | P0 | Fallback protects UX when systems are unavailable | Reduce robotic fallback tone further
Phase 6 | AI | Quality | Natural free-form conversation upgraded | Done | On main | P1 | Model-first flow replaced rigid menus | Continue real-world prompt tuning
Phase 7 | Security | Architecture | Security architecture doc created | Done | On main | P1 | System architecture doc exists | Maintain as system evolves
Phase 7 | Security | Architecture | Endpoint inventory doc created | Done | On main | P1 | Endpoint inventory exists | Update after new APIs
Phase 7 | Security | Compliance | NDPA/VAPT hardening plan created | Done | On main | P1 | Security roadmap doc exists | Execute the hardening backlog
Phase 7 | Security | API Docs | OpenAPI spec created | Done | On main | P1 | Swagger-importable YAML exists | Keep synchronized with routes
Phase 7 | Security | API Docs | In-app API docs page implemented | Done | On main | P1 | /dashboard/docs/api exists | Use as internal reference

## In Progress
Phase | Area | Workstream | Task | Status | Deployment State | Priority | Notes | Next Step
Phase 1 | Auth | Security | Password hashing and verification helpers added | In Progress | Local only | P0 | Auth hardening is in local worktree | Commit with next auth/backend batch
Phase 1B | Admin | Control Plane | Separate /admin control-plane shell implemented | In Progress | Local only | P0 | New admin route group and shell exist locally | Validate flow and ship with next backend batch
Phase 1B | Admin | Overview | Live admin overview API and page implemented | In Progress | Local only | P0 | Overview now reflects real org data and audit activity | Validate against live DB and deploy
Phase 1B | Admin | User Management | Workspace user admin page and API expansion implemented | In Progress | Local only | P0 | Admins can create, role-manage, and remove org users with founder lock rules | Validate and deploy
Phase 1B | Admin | Workspace Controls | Workspace settings admin page and API implemented | In Progress | Local only | P1 | Org settings are now split into admin control plane | Validate and deploy
Phase 1B | Admin | Security Controls | Admin security page implemented | In Progress | Local only | P1 | 2FA coverage, privileged users, and audit visibility are surfaced | Validate and deploy
Phase 1B | Admin | Platform Governance | Super-admin system page and workspace provisioning route implemented | In Progress | Local only | P0 | Founder can create stakeholder workspaces without giving up SUPER_ADMIN | Validate and deploy
Phase 12 | Tenant Lifecycle | Workspace Provisioning | Founder-controlled stakeholder workspace provisioning foundation started | In Progress | Local only | P0 | Super-admin can seed workspaces and initial admins, but acceptance and lifecycle are still incomplete | Validate and expand into full tenant lifecycle
Phase 12 | Tenant Lifecycle | Authorization | Founder lock and workspace-scoped admin boundaries started | In Progress | Local only | P0 | Role boundaries now exist in admin flows, but action-level RBAC is not complete | Extend into module-by-module permission enforcement
Phase 8 | HR | Backend Conversion | HR API routes added (employees, payroll, attendance, positions) | In Progress | Local only | P0 | Routes exist in local worktree | Apply migration, test, then commit
Phase 8 | HR | Frontend Rewire | HR page rewritten to call /api/hr/* | In Progress | Local only | P0 | UI is being moved off mock/local-only state | Validate with live DB
Phase 8 | HR | Data Quality | HR scorecard/compliance views present | In Progress | Local only | P1 | Support components exist locally | Finish polish and validation
Phase 8 | Projects | Backend Conversion | Projects API routes added | In Progress | Local only | P0 | /api/projects and /api/projects/tasks exist locally | Apply migration, test, then commit
Phase 8 | Projects | Frontend Rewire | Projects page rewritten to use live API | In Progress | Local only | P0 | Project board/task/timeline are wired toward live data | Validate with live DB
Phase 8 | Inventory | Backend Conversion | Inventory API routes added | In Progress | Local only | P0 | Products, stock, orders routes exist locally | Apply migration, test, then commit
Phase 8 | Inventory | Frontend Rewire | Inventory page rewritten to use live API | In Progress | Local only | P0 | Tables are wired toward live data | Validate with live DB
Phase 8 | Shared Backend | Seed Data | Module seed helper added for HR/Projects/Inventory | In Progress | Local only | P1 | Local seed helper exists | Keep only as controlled dev/demo behavior
Phase 8 | Shared Backend | Access Control | Org ownership checks added to new HR/Projects/Inventory routes | In Progress | Local only | P0 | Mutation routes were tightened locally | Ship with backend conversion commit
Phase 9 | Infrastructure | Database | Pending migration created for HR/Projects/Inventory backend | In Progress | Local only | P0 | Migration folder exists locally | Apply migration to active database

## Pending
Phase | Area | Workstream | Task | Status | Deployment State | Priority | Notes | Next Step
Phase 9 | Infrastructure | Database | Active DATABASE_URL is stable and reachable | Pending | Not complete | P0 | Recent Prisma migrate attempts failed with P1001 | Fix DB provider/credentials first
Phase 9 | Infrastructure | Deployment | Admin control-plane batch committed and pushed | Pending | Not started | P0 | New /admin shell and APIs are local only | Ship alongside backend conversion or in a clean isolated batch
Phase 9 | Infrastructure | Deployment | Render deployment synced with new admin control plane | Pending | Not started | P0 | Stakeholder admin experience is not live until deploy completes | Deploy after push and smoke test
Phase 9 | Infrastructure | Deployment | Local HR/Projects/Inventory backend work committed and pushed | Pending | Not started | P0 | Worktree is ahead of main | Commit a clean backend batch after DB validation
Phase 9 | Infrastructure | Deployment | Render deployment synced with latest local backend conversion | Pending | Not started | P0 | Render is behind current local backend work | Deploy after commit/push
Phase 10 | Integrations | Auth | Production Google OAuth credentials configured | Pending | Not complete | P1 | Code support exists, env still needs live values | Add production client ID/secret
Phase 10 | Integrations | Email | SMTP configured for real notifications and report delivery | Pending | Not complete | P1 | Nodemailer path exists | Add SMTP env values and test delivery
Phase 10 | Integrations | Uploads | Cloudinary configured for production uploads | Pending | Not complete | P1 | Upload path exists but depends on env | Add Cloudinary env values and test portal/gallery/docs
Phase 10 | Integrations | AI | Live AI provider keys configured | Pending | Partially complete | P0 | Provider routing exists but production keys may not be stable | Set and validate chosen providers
Phase 10 | Integrations | Payments | Paystack integration configured if required | Pending | Not complete | P2 | Env placeholders exist | Decide scope and implement if needed
Phase 11 | Quality | AI Quality | Continue tuning AI naturalness and business usefulness | Pending | Ongoing | P1 | AI is improved but still needs product-quality refinement | Use real user prompts and tighten responses
Phase 11 | Quality | Security | Execute remaining security hardening/VAPT backlog | Pending | Ongoing | P0 | Docs exist but many controls remain to implement | Run phased hardening plan
Phase 11 | Quality | Operations | Keep docs and OpenAPI spec aligned with shipped code | Pending | Ongoing | P1 | Docs now exist and need maintenance discipline | Update docs in every feature batch
Phase 11 | Quality | Release Discipline | Separate committed production-ready work from local experiments | Pending | Ongoing | P0 | Local worktree is carrying many in-progress changes | Ship smaller isolated batches
Phase 12 | Tenant Lifecycle | Workspace Provisioning | Invite acceptance flow for seeded users implemented | Pending | Not started | P0 | Stakeholder admins can be created, but acceptance/onboarding is not finished | Build invite acceptance and completion flow
Phase 12 | Tenant Lifecycle | Workspace Access | Multi-workspace membership and org switching implemented | Pending | Not started | P0 | Founder/support workflows will need to move across workspaces cleanly | Design membership model and switcher
Phase 12 | Tenant Lifecycle | Workspace Governance | Workspace suspension, archive, and restore controls implemented | Pending | Not started | P1 | You need a lifecycle for dormant or non-compliant stakeholder orgs | Add org status controls and UI
Phase 12 | Tenant Lifecycle | Entitlements | Org-level feature flags and lifecycle states implemented | Pending | Not started | P1 | Required for staged rollout and plan control | Add feature flag and org state model
Phase 12 | Tenant Lifecycle | Authorization | Action-level RBAC matrix enforced across modules | Pending | Not started | P0 | Current auth is stronger, but not yet a full action matrix | Define and enforce per-action permissions
Phase 13 | Commercial | Billing | Seat and entitlement model implemented | Pending | Not started | P1 | Stakeholder workspaces need plan-aware limits | Define seat model and enforcement
Phase 13 | Commercial | Billing | Billing and subscription admin console implemented | Pending | Not started | P1 | Admins need visibility into plan and seats | Build billing summary and controls
Phase 13 | Commercial | Feature Gating | Plan-aware feature gating implemented | Pending | Not started | P1 | Needed to sell multiple tiers without code forks | Add entitlements to routes and UI
Phase 13 | Commercial | Lifecycle | Trial, upgrade, and downgrade flows implemented | Pending | Not started | P2 | Commercial readiness improves with self-service lifecycle | Add commercial lifecycle rules
Phase 14 | Reliability | Observability | Production error tracking and alerting configured | Pending | Not started | P0 | You should know when auth, AI, uploads, or DB fail in production | Configure monitoring and alerting
Phase 14 | Reliability | Observability | Structured logs and uptime monitoring configured | Pending | Not started | P1 | Support and operations need visibility into live failures | Add log aggregation and uptime checks
Phase 14 | Reliability | Async Work | Background jobs and queue system implemented | Pending | Not started | P1 | Digests, webhooks, and retries should not depend on request-response timing | Add async job infrastructure
Phase 14 | Reliability | Recovery | Backup and restore workflow documented and tested | Pending | Not started | P0 | Production data safety is not optional | Define backup plan and run restore drills
Phase 14 | Reliability | Recovery | Incident response runbook operationalized | Pending | Not started | P1 | The docs exist, but the operating motion does not yet | Create and test response workflow
Phase 15 | Data Governance | Import/Export | CSV importers for CRM, HR, inventory, and accounting implemented | Pending | Not started | P1 | Real customers will want to move data in fast | Build import tools and mapping UX
Phase 15 | Data Governance | Import/Export | Admin export center for operational and compliance data implemented | Pending | Not started | P1 | Stakeholders will need consistent exports beyond isolated reports | Add central export surface
Phase 15 | Data Governance | Recovery | Soft delete and record recovery flows implemented | Pending | Not started | P1 | Accidental deletion without recovery will hurt trust | Add reversible delete patterns
Phase 15 | Data Governance | Compliance | Data retention and purge controls implemented | Pending | Not started | P1 | Needed for governance and NDPA discipline | Define retention policy and jobs
Phase 15 | Data Governance | Compliance | NDPA/privacy request workflow implemented | Pending | Not started | P1 | Privacy requests should be operational, not only documented | Add request handling workflow
Phase 15 | Data Governance | Governance | Approval center for sensitive actions implemented | Pending | Not started | P1 | High-risk actions need approvals and evidence | Build approval center and audit tie-in
Phase 15 | Data Governance | Branding | White-label and enterprise branding controls implemented | Pending | Not started | P2 | Important for polished stakeholder rollout, but not a launch blocker | Add branding controls later
Phase 16 | Support | Customer Success | In-product help center and onboarding content implemented | Pending | Not started | P2 | Users need a support surface that does not depend on you manually answering everything | Build help center and guides
Phase 16 | Support | Support Ops | Support impersonation with audit trail implemented | Pending | Not started | P1 | Support needs controlled access for troubleshooting | Add audited impersonation or support sessions
Phase 16 | Support | Customer Success | Customer usage and health analytics implemented | Pending | Not started | P2 | Useful for renewals and stakeholder expansion | Add adoption and health reporting
Phase 16 | Support | Communication | Release notes and changelog workflow implemented | Pending | Not started | P2 | Customers should see product progress clearly | Add changelog discipline
Phase 16 | Go-To-Market | Quality | Accessibility and mobile QA sweep completed | Pending | Not started | P1 | Pitching stakeholders on unstable mobile/accessibility experiences is risky | Run QA sweep and fix findings
Phase 16 | Go-To-Market | Readiness | Stakeholder pitch readiness gate completed | Pending | Not started | P0 | You need a formal go/no-go checklist before handing this to serious stakeholders | Use the pitch-readiness document as the gate
Phase 17 | Brand | Marketing Site | Landing page redesign completed | Pending | Not started | P2 | Current landing page is not yet strong enough for premium product positioning | Run a full brand and conversion redesign later
Phase 17 | Brand | Positioning | Product messaging and trust-signals upgraded | Pending | Not started | P2 | The product needs clearer premium positioning for stakeholders and buyers | Rewrite positioning and supporting sections

## Pitch Readiness
Tier | Area | Requirement | Status | Priority | Notes
Must Have | Platform Control | Founder remains the only permanent SUPER_ADMIN | In Progress | P0 | Policy and local enforcement exist; must be validated on live deploy
Must Have | Platform Control | Stakeholder admins are restricted to their own workspace | In Progress | P0 | Admin boundaries exist locally; validate on live deploy
Must Have | Platform Control | Admin pages are live on deployed environment | Pending | P0 | New control plane is local until committed and deployed
Must Have | Platform Control | Workspace admin user management works on deployed environment | Pending | P0 | Needs live validation after deploy
Must Have | Data and Backend | Database connection is stable and reachable | Pending | P0 | Current DB connectivity is the main blocker
Must Have | Data and Backend | Pending migrations are applied successfully | Pending | P0 | Required before broader live validation
Must Have | Data and Backend | Core module data persists correctly against live DB | Pending | P0 | HR, Projects, Inventory still need end-to-end live validation
Must Have | Security Baseline | Role boundaries are enforced server-side | In Progress | P0 | Improved locally; still needs broader module-by-module hardening
Must Have | Security Baseline | Audit logs capture admin-critical actions | In Progress | P0 | Admin actions now audit locally; validate and broaden coverage
Must Have | Product Stability | Critical pages do not throw runtime errors in demo path | In Progress | P0 | Production build passes; still validate deployed flow
Should Have Before Paid Pilot | Identity and Access | Invite acceptance flow for seeded users | Pending | P0 | Stakeholder onboarding needs completion flow
Should Have Before Paid Pilot | Identity and Access | Stable Google OAuth or clearly supported credentials flow | Pending | P1 | Decide the production sign-in path and validate it
Should Have Before Paid Pilot | Identity and Access | Full 2FA validation against live database | Pending | P1 | Route surface exists; live validation still needed
Should Have Before Paid Pilot | Production Integrations | SMTP configured and tested | Pending | P1 | Required for notifications and digests
Should Have Before Paid Pilot | Production Integrations | Cloudinary or equivalent upload storage configured and tested | Pending | P1 | Required for portal/docs/gallery upload credibility
Should Have Before Paid Pilot | Reliability | Error tracking configured | Pending | P0 | You need visibility into production failures
Should Have Before Paid Pilot | Reliability | Backup and restore plan tested | Pending | P0 | Production data safety must be operational
Should Have Before Paid Pilot | Governance | Security hardening backlog started in implementation | Pending | P1 | NDPA/VAPT should move from docs into code/ops
Pitch-Ready Next | Data Governance | CSV importers for CRM/HR/Inventory/Accounting | Pending | P1 | Important for real onboarding speed
Pitch-Ready Next | Data Governance | Export center for operational/compliance workflows | Pending | P1 | Stakeholders will ask for reliable exports
Pitch-Ready Next | Recovery | Soft delete and record recovery | Pending | P1 | Protects trust after mistakes
Pitch-Ready Next | Support | In-product help center | Pending | P2 | Reduces dependence on founder support
Pitch-Ready Next | Support | Support impersonation with audit trail | Pending | P1 | Important for troubleshooting and customer success
Pitch-Ready Next | Commercial | Billing and seat visibility for admins | Pending | P1 | Important as soon as pricing is formalized
Later | Enterprise | White-label and enterprise branding controls | Pending | P2 | Useful for premium deals but not first blocker
Later | Commercial | Advanced subscription self-service | Pending | P2 | Can follow initial controlled rollout
Later | Governance | Expanded approval center for sensitive actions | Pending | P2 | Important as complexity grows
Later | Brand | Landing page and marketing-site redesign | Pending | P2 | Important for conversion and brand perception, but not the first platform blocker