## Done
Phase | Area | Workstream | Task | Status | Deployment State | Priority | Notes | Next Step
Phase 0 | Foundation | Platform Setup | Next.js 16 app structure is in place | Done | On main | P0 | Public pages and dashboard shell already exist | Maintain and extend
Phase 0 | Foundation | Platform Setup | Prisma schema and Postgres integration are in place | Done | On main | P0 | Core relational data model exists | Keep schema synced with migrations
Phase 0 | Foundation | Build System | Production build switched to webpack for stability | Done | Local and expected for next deploy | P0 | Local build passes via webpack path | Commit and deploy with next backend batch
Phase 0 | Foundation | Documentation | Project dossier created | Done | On main | P1 | Snapshot-level project documentation exists | Keep updated after major releases
Phase 0 | Foundation | Documentation | Product overview created | Done | On main | P1 | Business-facing project summary exists | Refine for investor/client use if needed
Phase 0 | Foundation | Documentation | Technical handoff created | Done | On main | P1 | Developer-facing handoff doc exists | Update after backend shipping
Phase 0 | Foundation | Documentation | Platform readiness tracker expanded to full product scope | Done | Local only | P1 | Checklist now explicitly tracks missing platform layers like admin, tenant lifecycle, billing, observability, support, and enterprise governance | Keep updated as scope evolves
Phase 1 | Auth | Authentication | NextAuth credentials login implemented | Done | On main | P0 | Credentials flow exists | Keep testing against live DB
Phase 1 | Auth | Authentication | Google OAuth support path implemented | Done | On main | P1 | Provider support exists in code | Add production credentials
Phase 1 | Auth | Authentication | 2FA routes implemented | Done | Mostly local/in repo | P1 | Setup, verify, disable, verify-login routes exist | Validate end-to-end with live DB
Phase 1 | Auth | Authorization | Role model implemented (SUPER_ADMIN, ADMIN, USER) | Done | On main | P0 | Role enum and session role flow exist | Expand RBAC per module/action
Phase 2 | CRM | Core CRM | Contacts CRUD implemented | Done | On main | P0 | API and page support exist | Continue UX improvement
Phase 2 | CRM | Core CRM | Companies CRUD implemented | Done | On main | P0 | API and page support exist | Continue UX improvement
Phase 2 | CRM | Core CRM | Deals CRUD implemented | Done | On main | P0 | API and page support exist | Continue UX improvement
Phase 2 | CRM | Customization | Custom CRM field system implemented | Done | On main | P1 | Supports text, number, currency, date, select, multiselect, checkbox | Improve field editor UX
Phase 2 | CRM | Automation | CRM follow-up generation endpoint implemented | Done | On main | P1 | Follow-up generation route exists | Keep tuning AI quality
Phase 2 | CRM | Reporting | CRM reports and dashboard views implemented | Done | On main | P1 | Reporting surface exists | Improve accuracy/visual polish
Phase 3 | Accounting | Finance Core | Invoices CRUD implemented | Done | On main | P0 | Accounting API routes exist | Continue real-world validation
Phase 3 | Accounting | Finance Core | Expenses CRUD implemented | Done | On main | P0 | Accounting API routes exist | Continue real-world validation
Phase 3 | Accounting | Reporting | Report export routes implemented | Done | On main | P1 | Export and summary endpoints exist | Validate data accuracy with live DB
Phase 3 | Accounting | Reporting | Digest/reporting endpoints implemented | Done | On main | P1 | Digest and summary routes exist | Connect to SMTP for email delivery
Phase 4 | Operations | Ops Control | Ops command center implemented | Done | On main | P1 | Operations route/page exist | Continue UX and live data tuning
Phase 4 | Operations | Automation | Workflow endpoints implemented | Done | On main | P1 | Automation workflow support exists | Add more real workflows
Phase 4 | Operations | Automation | Playbooks implemented | Done | On main | P1 | Playbook route/page exist | Keep expanding playbook library
Phase 4 | Operations | Governance | Decision trails and rollback routes implemented | Done | On main | P1 | Decision trail and rollback endpoints exist | Continue auditability improvements
Phase 4 | Operations | Governance | Audit logging implemented | Done | On main | P0 | Audit helper and route exist | Broaden action coverage
Phase 4 | Operations | Integrations | Webhook endpoints implemented | Done | On main | P1 | Webhook route exists | Lock down and document secrets/rotation
Phase 5 | Portal | Client Collaboration | Client portal implemented | Done | On main | P1 | Portal routes, page, updates, docs, approvals exist | Improve production UX
Phase 5 | Portal | Client Collaboration | Portal updates implemented | Done | On main | P1 | Update routes exist | Continue UI polish
Phase 5 | Portal | Client Collaboration | Portal documents implemented | Done | On main | P1 | Document route exists | Finish real upload path with Cloudinary
Phase 5 | Portal | Client Collaboration | Portal approvals implemented | Done | On main | P1 | Approval route exists | Test approval flows against live DB
Phase 6 | AI | Assistant Core | /api/ai/chat implemented | Done | On main | P0 | Primary AI route exists | Keep prompt and tool quality improving
Phase 6 | AI | Assistant Core | /api/ai/conversations implemented | Done | On main | P1 | Conversation alias route exists | Use for future thread persistence
Phase 6 | AI | Provider Routing | OpenAI/Anthropic/Gemini provider routing implemented | Done | On main | P0 | Provider selection logic exists | Add/verify live keys
Phase 6 | AI | User Experience | Global AI coach/popover implemented | Done | On main | P1 | AI guide is embedded across pages | Refine guidance and humor balance
Phase 6 | AI | User Experience | AI guided navigation actions implemented | Done | On main | P1 | Model can route users to modules | Improve page-aware highlighting
Phase 6 | AI | Productivity | Email drafting implemented | Done | On main | P1 | Email mode exists | Improve draft templates per department
Phase 6 | AI | Reliability | Fallback behavior for provider/DB outages implemented | Done | On main | P0 | Fallback protects UX when systems are unavailable | Reduce robotic fallback tone further
Phase 6 | AI | Quality | Natural free-form conversation upgraded | Done | On main | P1 | Model-first flow replaced rigid menus | Continue real-world prompt tuning
Phase 7 | Security | Architecture | Security architecture doc created | Done | On main | P1 | System architecture doc exists | Maintain as system evolves
Phase 7 | Security | Architecture | Endpoint inventory doc created | Done | On main | P1 | Endpoint inventory exists | Update after new APIs
Phase 7 | Security | Compliance | NDPA/VAPT hardening plan created | Done | On main | P1 | Security roadmap doc exists | Execute the hardening backlog
Phase 7 | Security | API Docs | OpenAPI spec created | Done | On main | P1 | Swagger-importable YAML exists | Keep synchronized with routes
Phase 7 | Security | API Docs | In-app API docs page implemented | Done | On main | P1 | /dashboard/docs/api exists | Use as internal reference