## Master
Phase | Area | Workstream | Task | Status | Deployment State | Priority | Notes | Next Step
Phase 0 | Foundation | Platform Setup | Next.js 16 app structure is in place | Done | On main | P0 | Public pages and dashboard shell already exist | Maintain and extend
Phase 0 | Foundation | Platform Setup | Prisma schema and Postgres integration are in place | Done | On main | P0 | Core relational data model exists | Keep schema synced with migrations
Phase 0 | Foundation | Build System | Production build switched to webpack for stability | Done | Local and expected for next deploy | P0 | Local build passes via webpack path | Commit and deploy with next backend batch
Phase 0 | Foundation | Documentation | Project dossier created | Done | On main | P1 | Snapshot-level project documentation exists | Keep updated after major releases
Phase 0 | Foundation | Documentation | Product overview created | Done | On main | P1 | Business-facing project summary exists | Refine for investor/client use if needed
Phase 0 | Foundation | Documentation | Technical handoff created | Done | On main | P1 | Developer-facing handoff doc exists | Update after backend shipping
Phase 0 | Foundation | Documentation | Platform readiness tracker expanded to full product scope | Done | Local only | P1 | Checklist now explicitly tracks missing platform layers like admin, tenant lifecycle, billing, observability, support, and enterprise governance | Keep updated as scope evolves
Phase 1 | Auth | Authentication | NextAuth credentials login implemented | Done | On main | P0 | Credentials flow exists | Keep testing against live DB
Phase 1 | Auth | Authentication | Google OAuth support path implemented | Done | On main | P1 | Provider support exists in code | Add production credentials
Phase 1 | Auth | Authentication | 2FA routes implemented | Done | Mostly local/in repo | P1 | Setup, verify, disable, verify-login routes exist | Validate end-to-end with live DB
Phase 1 | Auth | Authorization | Role model implemented (SUPER_ADMIN, ADMIN, USER) | Done | On main | P0 | Role enum and session role flow exist | Expand RBAC per module/action
Phase 1 | Auth | Security | Password hashing and verification helpers added | In Progress | Local only | P0 | Auth hardening is in local worktree | Commit with next auth/backend batch
Phase 1B | Admin | Control Plane | Separate /admin control-plane shell implemented | In Progress | Local only | P0 | New admin route group and shell exist locally | Validate flow and ship with next backend batch
Phase 1B | Admin | Overview | Live admin overview API and page implemented | In Progress | Local only | P0 | Overview now reflects real org data and audit activity | Validate against live DB and deploy
Phase 1B | Admin | User Management | Workspace user admin page and API expansion implemented | In Progress | Local only | P0 | Admins can create, role-manage, and remove org users with founder lock rules | Validate and deploy
Phase 1B | Admin | Workspace Controls | Workspace settings admin page and API implemented | In Progress | Local only | P1 | Org settings are now split into admin control plane | Validate and deploy
Phase 1B | Admin | Security Controls | Admin security page implemented | In Progress | Local only | P1 | 2FA coverage, privileged users, and audit visibility are surfaced | Validate and deploy
Phase 1B | Admin | Platform Governance | Super-admin system page and workspace provisioning route implemented | In Progress | Local only | P0 | Founder can create stakeholder workspaces without giving up SUPER_ADMIN | Validate and deploy
Phase 2 | CRM | Core CRM | Contacts CRUD implemented | Done | On main | P0 | API and page support exist | Continue UX improvement
Phase 2 | CRM | Core CRM | Companies CRUD implemented | Done | On main | P0 | API and page support exist | Continue UX improvement
Phase 2 | CRM | Core CRM | Deals CRUD implemented | Done | On main | P0 | API and page support exist | Continue UX improvement
Phase 2 | CRM | Customization | Custom CRM field system implemented | Done | On main | P1 | Supports text, number, currency, date, select, multiselect, checkbox | Improve field editor UX
Phase 2 | CRM | Automation | CRM follow-up generation endpoint implemented | Done | On main | P1 | Follow-up generation route exists | Keep tuning AI quality
Phase 2 | CRM | Reporting | CRM reports and dashboard views implemented | Done | On main | P1 | Reporting surface exists | Improve accuracy/visual polish
Phase 3 | Accounting | Finance Core | Invoices CRUD implemented | Done | On main | P0 | Accounting API routes exist | Continue real-world validation
Phase 3 | Accounting | Finance Core | Expenses CRUD implemented | Done | On main | P0 | Accounting API routes exist | Continue real-world validation
Phase 3 | Accounting | Reporting | Report export routes implemented | Done | On main | P1 | Export and summary endpoints exist | Validate data accuracy with live DB
Phase 3 | Accounting | Reporting | Digest/reporting endpoints implemented | Done | On main | P1 | Digest and summary routes exist | Connect to SMTP for email delivery
Phase 4 | Operations | Ops Control | Ops command center implemented | Done | On main | P1 | Operations route/page exist | Continue UX and live data tuning
Phase 4 | Operations | Automation | Workflow endpoints implemented | Done | On main | P1 | Automation workflow support exists | Add more real workflows
Phase 4 | Operations | Automation | Playbooks implemented | Done | On main | P1 | Playbook route/page exist | Keep expanding playbook library
Phase 4 | Operations | Governance | Decision trails and rollback routes implemented | Done | On main | P1 | Decision trail and rollback endpoints exist | Continue auditability improvements
Phase 4 | Operations | Governance | Audit logging implemented | Done | On main | P0 | Audit helper and route exist | Broaden action coverage
Phase 4 | Operations | Integrations | Webhook endpoints implemented | Done | On main | P1 | Webhook route exists | Lock down and document secrets/rotation
Phase 5 | Portal | Client Collaboration | Client portal implemented | Done | On main | P1 | Portal routes, page, updates, docs, approvals exist | Improve production UX
Phase 5 | Portal | Client Collaboration | Portal updates implemented | Done | On main | P1 | Update routes exist | Continue UI polish
Phase 5 | Portal | Client Collaboration | Portal documents implemented | Done | On main | P1 | Document route exists | Finish real upload path with Cloudinary
Phase 5 | Portal | Client Collaboration | Portal approvals implemented | Done | On main | P1 | Approval route exists | Test approval flows against live DB
Phase 6 | AI | Assistant Core | /api/ai/chat implemented | Done | On main | P0 | Primary AI route exists | Keep prompt and tool quality improving
Phase 6 | AI | Assistant Core | /api/ai/conversations implemented | Done | On main | P1 | Conversation alias route exists | Use for future thread persistence
Phase 6 | AI | Provider Routing | OpenAI/Anthropic/Gemini provider routing implemented | Done | On main | P0 | Provider selection logic exists | Add/verify live keys
Phase 6 | AI | User Experience | Global AI coach/popover implemented | Done | On main | P1 | AI guide is embedded across pages | Refine guidance and humor balance
Phase 6 | AI | User Experience | AI guided navigation actions implemented | Done | On main | P1 | Model can route users to modules | Improve page-aware highlighting
Phase 6 | AI | Productivity | Email drafting implemented | Done | On main | P1 | Email mode exists | Improve draft templates per department
Phase 6 | AI | Reliability | Fallback behavior for provider/DB outages implemented | Done | On main | P0 | Fallback protects UX when systems are unavailable | Reduce robotic fallback tone further
Phase 6 | AI | Quality | Natural free-form conversation upgraded | Done | On main | P1 | Model-first flow replaced rigid menus | Continue real-world prompt tuning
Phase 7 | Security | Architecture | Security architecture doc created | Done | On main | P1 | System architecture doc exists | Maintain as system evolves
Phase 7 | Security | Architecture | Endpoint inventory doc created | Done | On main | P1 | Endpoint inventory exists | Update after new APIs
Phase 7 | Security | Compliance | NDPA/VAPT hardening plan created | Done | On main | P1 | Security roadmap doc exists | Execute the hardening backlog
Phase 7 | Security | API Docs | OpenAPI spec created | Done | On main | P1 | Swagger-importable YAML exists | Keep synchronized with routes
Phase 7 | Security | API Docs | In-app API docs page implemented | Done | On main | P1 | /dashboard/docs/api exists | Use as internal reference
Phase 8 | HR | Backend Conversion | HR API routes added (employees, payroll, attendance, positions) | In Progress | Local only | P0 | Routes exist in local worktree | Apply migration, test, then commit
Phase 8 | HR | Frontend Rewire | HR page rewritten to call /api/hr/* | In Progress | Local only | P0 | UI is being moved off mock/local-only state | Validate with live DB
Phase 8 | HR | Data Quality | HR scorecard/compliance views present | In Progress | Local only | P1 | Support components exist locally | Finish polish and validation
Phase 8 | Projects | Backend Conversion | Projects API routes added | In Progress | Local only | P0 | /api/projects and /api/projects/tasks exist locally | Apply migration, test, then commit
Phase 8 | Projects | Frontend Rewire | Projects page rewritten to use live API | In Progress | Local only | P0 | Project board/task/timeline are wired toward live data | Validate with live DB
Phase 8 | Inventory | Backend Conversion | Inventory API routes added | In Progress | Local only | P0 | Products, stock, orders routes exist locally | Apply migration, test, then commit
Phase 8 | Inventory | Frontend Rewire | Inventory page rewritten to use live API | In Progress | Local only | P0 | Tables are wired toward live data | Validate with live DB
Phase 8 | Shared Backend | Seed Data | Module seed helper added for HR/Projects/Inventory | In Progress | Local only | P1 | Local seed helper exists | Keep only as controlled dev/demo behavior
Phase 8 | Shared Backend | Access Control | Org ownership checks added to new HR/Projects/Inventory routes | In Progress | Local only | P0 | Mutation routes were tightened locally | Ship with backend conversion commit
Phase 9 | Infrastructure | Database | Pending migration created for HR/Projects/Inventory backend | In Progress | Local only | P0 | Migration folder exists locally | Apply migration to active database
Phase 9 | Infrastructure | Database | Active DATABASE_URL is stable and reachable | Pending | Not complete | P0 | Recent Prisma migrate attempts failed with P1001 | Fix DB provider/credentials first
Phase 9 | Infrastructure | Deployment | Admin control-plane batch committed and pushed | Pending | Not started | P0 | New /admin shell and APIs are local only | Ship alongside backend conversion or in a clean isolated batch
Phase 9 | Infrastructure | Deployment | Render deployment synced with new admin control plane | Pending | Not started | P0 | Stakeholder admin experience is not live until deploy completes | Deploy after push and smoke test
Phase 9 | Infrastructure | Deployment | Local HR/Projects/Inventory backend work committed and pushed | Pending | Not started | P0 | Worktree is ahead of main | Commit a clean backend batch after DB validation
Phase 9 | Infrastructure | Deployment | Render deployment synced with latest local backend conversion | Pending | Not started | P0 | Render is behind current local backend work | Deploy after commit/push
Phase 10 | Integrations | Auth | Production Google OAuth credentials configured | Pending | Not complete | P1 | Code support exists, env still needs live values | Add production client ID/secret
Phase 10 | Integrations | Email | SMTP configured for real notifications and report delivery | Pending | Not complete | P1 | Nodemailer path exists | Add SMTP env values and test delivery
Phase 10 | Integrations | Uploads | Cloudinary configured for production uploads | Pending | Not complete | P1 | Upload path exists but depends on env | Add Cloudinary env values and test portal/gallery/docs
Phase 10 | Integrations | AI | Live AI provider keys configured | Pending | Partially complete | P0 | Provider routing exists but production keys may not be stable | Set and validate chosen providers
Phase 10 | Integrations | Payments | Paystack integration configured if required | Pending | Not complete | P2 | Env placeholders exist | Decide scope and implement if needed
Phase 11 | Quality | AI Quality | Continue tuning AI naturalness and business usefulness | Pending | Ongoing | P1 | AI is improved but still needs product-quality refinement | Use real user prompts and tighten responses
Phase 11 | Quality | Security | Execute remaining security hardening/VAPT backlog | Pending | Ongoing | P0 | Docs exist but many controls remain to implement | Run phased hardening plan
Phase 11 | Quality | Operations | Keep docs and OpenAPI spec aligned with shipped code | Pending | Ongoing | P1 | Docs now exist and need maintenance discipline | Update docs in every feature batch
Phase 11 | Quality | Release Discipline | Separate committed production-ready work from local experiments | Pending | Ongoing | P0 | Local worktree is carrying many in-progress changes | Ship smaller isolated batches
Phase 12 | Tenant Lifecycle | Workspace Provisioning | Invite acceptance flow for seeded users implemented | In Progress | Local only | P0 | Invite issuance, lookup, re-invite, and signup completion now exist locally | Deploy and smoke-test stakeholder onboarding flow
Phase 12 | Tenant Lifecycle | Workspace Access | Multi-workspace membership and org switching implemented | Pending | Not started | P0 | Founder/support workflows will need to move across workspaces cleanly | Design membership model and switcher
Phase 12 | Tenant Lifecycle | Workspace Governance | Workspace suspension, archive, and restore controls implemented | Pending | Not started | P1 | You need a lifecycle for dormant or non-compliant stakeholder orgs | Add org status controls and UI
Phase 12 | Tenant Lifecycle | Entitlements | Org-level feature flags and lifecycle states implemented | Pending | Not started | P1 | Required for staged rollout and plan control | Add feature flag and org state model
Phase 12 | Tenant Lifecycle | Authorization | Action-level RBAC matrix enforced across modules | Pending | Not started | P0 | Current auth is stronger, but not yet a full action matrix | Define and enforce per-action permissions
Phase 13 | Commercial | Billing | Seat and entitlement model implemented | Pending | Not started | P1 | Stakeholder workspaces need plan-aware limits | Define seat model and enforcement
Phase 13 | Commercial | Billing | Billing and subscription admin console implemented | Pending | Not started | P1 | Admins need visibility into plan and seats | Build billing summary and controls
Phase 13 | Commercial | Feature Gating | Plan-aware feature gating implemented | Pending | Not started | P1 | Needed to sell multiple tiers without code forks | Add entitlements to routes and UI
Phase 13 | Commercial | Lifecycle | Trial, upgrade, and downgrade flows implemented | Pending | Not started | P2 | Commercial readiness improves with self-service lifecycle | Add commercial lifecycle rules
Phase 14 | Reliability | Observability | Production error tracking and alerting configured | Pending | Not started | P0 | You should know when auth, AI, uploads, or DB fail in production | Configure monitoring and alerting
Phase 14 | Reliability | Observability | Structured logs and uptime monitoring configured | Pending | Not started | P1 | Support and operations need visibility into live failures | Add log aggregation and uptime checks
Phase 14 | Reliability | Async Work | Background jobs and queue system implemented | Pending | Not started | P1 | Digests, webhooks, and retries should not depend on request-response timing | Add async job infrastructure
Phase 14 | Reliability | Recovery | Backup and restore workflow documented and tested | Pending | Not started | P0 | Production data safety is not optional | Define backup plan and run restore drills
Phase 14 | Reliability | Recovery | Incident response runbook operationalized | Pending | Not started | P1 | The docs exist, but the operating motion does not yet | Create and test response workflow
Phase 15 | Data Governance | Import/Export | CSV importers for CRM, HR, inventory, and accounting implemented | Pending | Not started | P1 | Real customers will want to move data in fast | Build import tools and mapping UX
Phase 15 | Data Governance | Import/Export | Admin export center for operational and compliance data implemented | Pending | Not started | P1 | Stakeholders will need consistent exports beyond isolated reports | Add central export surface
Phase 15 | Data Governance | Recovery | Soft delete and record recovery flows implemented | Pending | Not started | P1 | Accidental deletion without recovery will hurt trust | Add reversible delete patterns
Phase 15 | Data Governance | Compliance | Data retention and purge controls implemented | Pending | Not started | P1 | Needed for governance and NDPA discipline | Define retention policy and jobs
Phase 15 | Data Governance | Compliance | NDPA/privacy request workflow implemented | Pending | Not started | P1 | Privacy requests should be operational, not only documented | Add request handling workflow
Phase 15 | Data Governance | Governance | Approval center for sensitive actions implemented | Pending | Not started | P1 | High-risk actions need approvals and evidence | Build approval center and audit tie-in
Phase 15 | Data Governance | Branding | White-label and enterprise branding controls implemented | Pending | Not started | P2 | Important for polished stakeholder rollout, but not a launch blocker | Add branding controls later
Phase 16 | Support | Customer Success | In-product help center and onboarding content implemented | Pending | Not started | P2 | Users need a support surface that does not depend on you manually answering everything | Build help center and guides
Phase 16 | Support | Support Ops | Support impersonation with audit trail implemented | Pending | Not started | P1 | Support needs controlled access for troubleshooting | Add audited impersonation or support sessions
Phase 16 | Support | Customer Success | Customer usage and health analytics implemented | Pending | Not started | P2 | Useful for renewals and stakeholder expansion | Add adoption and health reporting
Phase 16 | Support | Communication | Release notes and changelog workflow implemented | Pending | Not started | P2 | Customers should see product progress clearly | Add changelog discipline
Phase 16 | Go-To-Market | Quality | Accessibility and mobile QA sweep completed | Pending | Not started | P1 | Pitching stakeholders on unstable mobile/accessibility experiences is risky | Run QA sweep and fix findings
Phase 16 | Go-To-Market | Readiness | Stakeholder pitch readiness gate completed | Pending | Not started | P0 | You need a formal go/no-go checklist before handing this to serious stakeholders | Use the pitch-readiness document as the gate
Phase 17 | Brand | Marketing Site | Landing page redesign completed | Pending | Not started | P2 | Current landing page is not yet strong enough for premium product positioning | Run a full brand and conversion redesign later
Phase 17 | Brand | Positioning | Product messaging and trust-signals upgraded | Pending | Not started | P2 | The product needs clearer premium positioning for stakeholders and buyers | Rewrite positioning and supporting sections